## Sheet1
UNIFORM STATUS OF FUNDS SPREADSHEET FOR: DATE: |  |  |  | City of Harlowton Phase 3 Water System Improvements Project | [20 empty] | 2026-08-05 21:24
| Funding Source: TSEP |  |  |  | Funding Source: CDBG |  |  |  | Funding Source: SRF A Loan |  |  |  | Funding Source: SRF B Loan |  |  |  | Funding Source: WRDA (Section 595) |  |  |  | Funding Source: Local |  |  |  | Total Budget
ADMINISTRATIVE/ FINANCIAL COSTS: | Budgeted | Previously Expended | Amount of Draw | Balance Remaining | Budgeted | Previously Expended | Amount of Draw | Balance Remaining | Budgeted | Previously Expended | Amount of Draw | Balance Remaining | Budgeted | Previously Expended | Amount of Draw | Balance Remaining | Budgeted | Previously Expended | Amount of Draw | Balance Remaining | Budgeted | Previously Expended | Amount of Draw | Balance Remaining | Budgeted | Expended | Balance
Personnel Costs | 0 |  |  | 0 | 0 |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0
Office Costs | 948.6 | 948.6 |  | 0 | 0 |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 948.6 | 948.6 | 0
Professional Services |  |  |  | 0 |  |  |  | 0 | 10221 | 10221 |  | 0 | 24449 | 24449 |  | 0 |  |  |  | 0 |  |  |  | 0 | 34670 | 34670 | 0
Legal Costs | 0 |  |  | 0 | 0 |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0
Audit Fees |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0 |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0
Travel & Training | 262.73 | 262.73 |  | 0 | 281.34 | 281.34 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 544.07 | 544.07 | 0
Loan Reserves (includes payoff of reserves from previous SRF loans) |  |  |  | 0 |  |  |  | 0 | 25468 | 25468 |  | 0 | 12725 | 12725 |  | 0 |  |  |  | 0 |  |  |  | 0 | 38193 | 38193 | 0
Interim Interest |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0
Bond Counsel |  |  |  | 0 |  |  |  | 0 | 5000 | 5000 |  | 0 | 5000 | 5000 |  | 0 |  |  |  | 0 |  |  |  | 0 | 10000 | 10000 | 0
|  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0
US Bank Interest Charge for BAN |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 538.21 | 538.21 |  | 0 |  |  |  | 0 |  |  |  | 0 | 538.21 | 538.21 | 0
Total Administrative Costs | 1211.33 | 1211.33 | 0 | 0 | 281.34 | 281.34 | 0 | 0 | 40689 | 40689 | 0 | 0 | 42712.21 | 42712.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84893.88 | 84893.88 | 0
ACTIVITY COSTS: | [26 empty] | 0
Engineering (Grant Writing & PER) |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 9405 | 9405 |  | 0 |  |  |  | 0 |  |  |  | 0 | 9405 | 9405 | 0
Engineering Design |  |  |  | 0 |  |  |  | 0 | 24716 | 24716 |  | 0 | 121447 | 121447 |  | 0 |  |  |  | 0 |  |  |  | 0 | 146163 | 146163 | 0
Construction Engineering Services |  |  |  | 0 |  |  |  | 0 | 140801 | 140801 |  | 0 | 2819 | 2819 |  | 0 | 49277.57 | 49277.57 |  | 0 |  |  |  | 0 | 192897.57 | 192897.57 | 0
Construction | 748788.67 | 748788.67 |  | 0 | 449718.66 | 449718.66 |  | 0 | 157620 | 157620 |  | 0 | 145915.29 | 145915.29 |  | 0 | 126272.43 | 126272.43 |  | 0 | 6765.88 | 6765.88 |  | 0 | 1635080.93 | 1635080.93 | 0
Construction (Water Meters) |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 48416.5 | 20867 | 27549.5 | 0 | 64450 | 62599.6 | 1850.4 | 0 |  |  |  | 0 | 112866.5 | 112866.5 | 0
Construction (South Well Rehab) |  |  |  | 0 |  |  |  | 0 | 28674 | 28674 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 28674 | 28674 | 0
Liquid Engineering (Water Tank) |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 11700 | 11700 |  | 0 |  |  |  | 0 |  |  |  | 0 | 11700 | 11700 | 0
Contingency |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0 |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0
Construction (Pritchard Well) |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 10085 | 10085 |  | 0 |  |  |  | 0 |  |  |  | 0 | 10085 | 10085 | 0
|  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0
Total Activity Costs | 748788.67 | 748788.67 | 0 | 0 | 449718.66 | 449718.66 | 0 | 0 | 351811 | 351811 | 0 | 0 | 349787.79 | 322238.29 | 27549.5 | 0 | 240000 | 238149.6 | 1850.4 | 0 | 6765.88 | 6765.88 | 0 | 0 | 2146872 | 2146872 | 0
TOTAL PROJECT COSTS | 750000 | 750000 | 0 | 0 | 450000 | 450000 | 0 | 0 | 392500 | 392500 | 0 | 0 | 392500 | 364950.5 | 27549.5 | 0 | 240000 | 238149.6 | 1850.4 | 0 | 6765.88 | 6765.88 | 0 | 0 | 2231765.88 | 2231765.88 | 0
Copy and submit to the applicable funding agency with each drawdown request. |  |  |  | 750000 |  |  |  | 450000 |  |  |  | 392500 |  |  |  | 392500 |  |  |  | 240000 |  |  |  | 6765.88 | 2026-08-05 | 100%
Note: The $132,926 Bond Anticipation Note for Preliminary Engineering work will be paid out of the WRF B Loan
Note: Debt Service Reserve amount is broken down on the combined for the three outstanding loans
Note: The $132,096 for the BAN Payoff includes $120,985 for engineering design and $11,941 for grant administration charged to project thru April 16, 2016
Note: $25,468 payoff of SRF reserve from the A loan is shown as a Miscellaneous expense on the A loan disbursement report
Note: 8/5/2016 Moved $565.00 from Contingency to Construction line item for Wilting invoice date 6/2016 (EP)
Note: Wilting Invoice from 6-16 taken out of SRF A Construction on 8/5 for August Draw (EP)
Note: $68,674 not included in SRF draw request #1. Submitted in Draw #2
Note: September 12, 2016 - Council approves Change Order #1 increase Construction Contract from 1,244,405 to $1,536,238 and $76,577.75 was moved from Contingency to the SRF B loan Construction budget
Note: October 19, 2016 - Transferred $11,700 from SRF B Contingency to Liguid Engineering (water tank) line item budget
Note: October 19, 2016 - Transferred $9,405 from SRF B Contingency to Engineering Grant Writing and PER - Authorization received from Anna Miller
Note: October 24, 2016 - Transferred $3,650 from SRF B loan contingency and $47,050 from WRDA Construction Water Meters contigency to Construction Engineering Services
Note: February 6, 2017- Transferred $2,227.57 from WRDA Construction to Construction Engineering Services
Note: March 8, 2017 added Line Item for Pritchard Well construction. Transferred $92,81.00 from SRF Contingency to Construction (Pritchard Well) (EP)
Note: March 27, 2017 Transferred $804.00 from SRF Contingency to Construction (Pritchard Well) and $326 from contingency to professional services (EP)
Note: July 12, 2017: Budget change request
CDBG Budget: Move $2,500 (Peronnel: $1,000, office: $500, & legal: $500, Travel: $218.34) From administrative activity costs to Construction
TSEP Budget: Move $2,500 (Peronnel: $551.40, travel $262.73: $500, & Legal: $237) From administrative activity costs to Construction
Note: July 18, 2017: Moved $1,056 from Professional Serives, $1,899 from engineering design, $1199 from Construction engineering to Construction in SRF A
Note: July 18, 2017: Moved $3,961 from contingency to Water Meters in SRF B
Note: July 18, 2017: Moved $831 from construction engineering to construction in SRF b
Note: July 18, 2017: Moved $3,166 from Audit fees water meters and $4,833.50 to construction in SRF B. City to cover Audit fees
Note: July 18, 2017: Moved $52,767.79 from contingency to construction in SRF B

## Note
Note: The $132,926 Bond Anticipation Note for Preliminary Engineering work will be paid out of the WRF B Loan
Note: Debt Service Reserve amount is broken down on the combined for the three outstanding loans
Note: The $132,096 for the BAN Payoff includes $120,985 for engineering design and $11,941 for grant administration charged to project thru April 16, 2016
Note: $25,468 payoff of SRF reserve from the A loan is shown as a Miscellaneous expense on the A loan disbursement report
Note: 8/5/2016 Moved $565.00 from Contingency to Construction line item for Wilting invoice date 6/2016 (EP)
Note: Wilting Invoice from 6-16 taken out of SRF A Construction on 8/5 for August Draw (EP)
Note: $68,674 not included in SRF draw request #1. Submitted in Draw #2
Note: September 12, 2016 - Council approves Change Order #1 increase Construction Contract from 1,244,405 to $1,536,238 and $76,577.75 was moved from Contingency to the SRF B loan Construction budget
Note: October 19, 2016 - Transferred $11,700 from SRF B Contingency to Liguid Engineering (water tank) line item budget
Note: October 19, 2016 - Transferred $9,405 from SRF B Contingency to Engineering Grant Writing and PER - Authorization received from Anna Miller
Note: October 24, 2016 - Transferred $3,650 from SRF B loan contingency and $47,050 from WRDA Construction Water Meters contigency to Construction Engineering Services
Note: February 6, 2017- Transferred $2,227.57 from WRDA Construction to Construction Engineering Services
Note: March 8, 2017 added Line Item for Pritchard Well construction. Transferred $92,81.00 from SRF Contingency to Construction (Pritchard Well) (EP)
Note: March 27, 2017 Transferred $804.00 from SRF Contingency to Construction (Pritchard Well) and $326 from contingency to professional services (EP)
Note: July 12, 2017: Budget change request
CDBG Budget: Move $2,500 (Peronnel: $1,000, office: $500, & legal: $500, Travel: $218.34) From administrative activity costs to Construction
TSEP Budget: Move $2,500 (Peronnel: $551.40, travel $262.73: $500, & Legal: $237) From administrative activity costs to Construction
Note: July 18, 2017: Moved $1,056 from Professional Serives, $1,899 from engineering design, $1199 from Construction engineering to Construction in SRF A
Note: July 18, 2017: Moved $3,961 from contingency to Water Meters in SRF B
Note: July 18, 2017: Moved $381 from construction engineering to construction in SRF b
Note: July 18, 2017: Moved $3,166 from Audit fees water meters and $4,833.50 to construction in SRF B. City to cover Audit fees
Note: July 18, 2017: Moved $52,767.79 from contingency to construction in SRF B